ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	3

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	4

4.2.	Specific work	4

4.3.	Project management	6

5.	LOGISTICS AND TIMING	7

5.1.	Location	7

5.2.	Start date & Period of implementation of tasks	7

6.	REQUIREMENTS	7

6.1.	Staff	7

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the Contractor	7

6.4.	Equipment	8

7.	REPORTS	8

7.1.	Reporting requirements	8

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

The Former Yugoslav Republic of Macedonia.

## Contracting Authority

## Faculty of Electrical Engineering and Information Technologies of   Ss. Cyril  and Methodius University in Skopje.

## Country background

FYROM is a candidate country for membership expecting commencement of membership negotiations. The next phase in the accession process is acquiring negotiation date for European Union membership.

The negotiation process of the Republic of Macedonia for EU membership will signify completion of the approximation process to the European Union, adoption of its benefits and values as well as complete adaptation of the Macedonian institutions towards functioning to that of the Union institutions. The negotiations will also signify establishing grounds and preparation for a successful functioning of the Republic of Macedonia as a Union Member State. In February 2008, the Council of Ministers of the European Union adopted the 2008 Accession Partnership of the Republic of Macedonia. The negotiations as a comprehensive dynamic undertaking require full preparation of the state authorities and institutions as well as of the structures established for coordination and conducting negotiations prior to the commencement of the negotiations themselves.

## Current situation in the sector

- The Balkan Med (BM) region is facing the challenge of sustaining and increasing the growth of PV systems that is endangered by several barriers and their unpredictable nature. This is especially important in the built environment as member states are developing plans to increase the number of Nearly Zero Energy Buildings (NZEB), which most probably employ PV’s, in order to reach their 2030 climate change targets.

- The project approach hasn’t been applied before in BM region. Most outputs are novel worldwide (e.g specialized tools) as well. A transnational approach is needed as the climate change problem faces no borders and a unified approach will multiply positive effects. Moreover, the region’s electrical grids are already interconnected with high interdependence and will be even more in the future.

- As the number of NZEBs increase, PV integration in the distribution grids of BM region will be very difficult, unless buildings become more grid-friendly and policies/regulations are suitably adapted.

- In the above context, the overall objective of project is to enhance the penetration of PV’s in built environment. This will be achieved by using storage, which will transform the building into a more predictable power source. With the high solar potential of the BM region and the decreasing cost of PV/storage systems, such a solution is becoming cost-efficient as well Project aims to change the way buildings with PV’s are treated (i.e. selling energy to grid) and instead conceptualize them as systems that must efficiently interact with grids. Also, it aims to alleviate the above barriers and pave the way for unobstructive NZEB development.

## Related programmes and other donor activities

N/A

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

1) An innovative management scheme of PV + storage hybrid, making buildings grid-friendlier;

2) A generalized model capable to assess alternative policies related to implementation of such hybrids;

3) An online user-friendly tool able to provide a good first estimate of the profitability of such systems under a specified policy, targeting prospective investors and stakeholders;

4) An advanced tool able to evaluate multiple policy scenarios, targeting policy makers;

5) Set of joint regulation recommendations in the form of roadmap for BM region, targeting grid operators and relevant stakeholders/engineers;

6) Set of joint policy recommendations targeting mainly policy makers and interested stakeholders;

7) Organization and implementation of a project  meeting , national workshop and an International scientific conference to present  the  results of the projects;

8) The project final data project will be published in an Open-access journal.

## Purpose

The successful Service provider will have responsibility for preparation and management of all logistical issues and arrangements related to hosting a successful and professional Meetings.

A total of two (2) meetings/workshops/ are expected to be conducted and managed by the successful Contractor. The meetings will take place in Skopje. The service provider should also ensure to provide a participation of the Contracting Authority to a International Conference in the Balkan-Med region countries and publishing of project final data in one science journal with an Open-access.

## Results to be achieved by the Contractor

The Contractor should successfully organize all detail listed services in section 4, according to the specific requirements detailed in the same section of this document and should submit the required report, described in section 7.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- Clear understanding of the contract objectives and purposes by the Contractor;

- Full cooperation between the Contracting Authority and the Contractor in view to fulfil the tasks on time, with high quality and within the budget limitation.

## Risks

Potential risks to the successful implementation of the contract include:

- Lack of communication and logistical coordination between the Contractor and the Contracting Authority. In order to avoid this risk, the Contractor should show initiative and maintain continuous contact with the relevant representatives of the Contracting Authority.

- Insufficient quality of the services provided by the Contractor experts and suppliers. In order to avoid this risk the Contractor should use the most reliable and experienced staff/service providers on its disposal.

# SCOPE OF THE WORK

## General

### Description of the assignment

The aim of this contract is necessary services and overall logistical coordination for the organization of the events and publication of the project results mentioned in p. 2.2. The Contractor will have to provide a variety of professional services, such as rent of hall, rent of audio/video equipment, catering services, and consultancy for accommodation for participants and team members, preparation of consumables for events, providing of international conferences and national fair of energy technologies and journal for publishing the project results.

Geographical area to be covered

Skopje, FYROM and Balkan Med region countries.

### Target groups

- Expert staff involved in project implementation;

- Participants in project events – stakeholders and academia, representatives of project partners;

- Educational institutions;

- Representatives of the national and regional media;

- Local community members in the project partners country;

## Specific work

- This section individually describes the specific services to be provided by the Contractor within the implementation of project “PV-ESTIA – Enhancing storage integration in buildings with Photovoltaics”. The Contractor should coordinate and receive prior approval from the Contracting Authority regarding important issues related to the organization of the events such as venue, equipment, menu, logistics, accommodation, etc.

Task 1: Organization of a national workshop in Skopje

| Time (duration)/place: | Duration of the event: one day in total. Forecast period for conduct of the event: March 2018 in Skopje. The contractor will be timely notified about the exact date of the workshop. |
| --- | --- |
| Service 1.1: | Provision of venue |
| Service description: | A formal conference hall, preferably at a central location in Skopje. The premises should be rented for the whole duration of the event. Conference hall capacity: minimum 50 people. In addition to the conference hall, a separate hall/lobby should be reserved in the same location for catering. The space for catering should be enough to accommodate all conference participants during coffee and lunch breaks. Multimedia projector and screen, appropriate in size and with technical specifications suitable for the type and venue of the event. Microphone and Speakers. Promotion of the event and full logistic. The booking of space has to be made after proposal of at least 2 options of halls and approval of one of them by the Contracting Authority. |
| Service 1.2: | Catering for the workshop |
| Service description: | - Organization and payment of one coffee break for minimum 50 people at the venue of the workshop. Minimum content of the menu for coffee break for each participant - coffee / tea-standard quantity, mineral water - 500 ml/ Soft drink - 250 ml, crackers and cookies - 200 g. - Organization and payment of lunch for minimum 50 people. Buffet style. The catering should comprise the following items for each guest: 1 cup of coffee or tea; 1 small bottle of mineral water (minimum 500 ml) and 1 small bottle/can of soft drink (minimum 300 ml); At least 5 serving pieces of warm cocktail snacks, including vegetarian options; At least 5 serving pieces of cold cocktail snacks, including vegetarian options; At least 4 pieces of cocktail desserts; At least 1 fresh fruit. The Contractor should prepare at least 3 versions of the lunch menu. The menus should be sent by the Contractor to the Contracting Authority for approval at least 5 working days prior to the meeting. The catering services should include professional staff for serving of the cocktail drinks and snacks; |

Task 2: Organization of the project meeting in Skopje

| Time (duration)/place: | Duration of the event three days in total. Forecast period for conduct of the event: February 2019 in Skopje. The contractor will be timely notified about the exact date of the workshop. |
| --- | --- |
| Service 1.1: | Provision of venue |
| Service description: | Assistance and consultancy to the Contracting Authority for providing a hotel accommodation for 2-3 night in single/double rooms (up to 15 people) in a minimum of three stars hotel in Skopje with included breakfast (at least 2 options of hotels and approval of one of them by the Contracting Authority; hotel should have Wi-Fi and parking space). Organization of the project meeting should be done in the hotel approved by the Contracting Authority. Please note that the budget of this contract refers only to assistance and consultancy services for providing a hotel accommodation to the project partners. Accommodation expenses will be paid by the each project partner after their approval. |
| Service 1.2: | Catering for the meeting in approved hotel by the Contracting Authority |
| Service description: | - Organization and payment of lunch for two days for minimum 20 people. - Buffet style. The catering should comprise the following items for each guest: 1 cup of coffee or tea; 1 small bottle of mineral water (minimum 500 ml) and 1 small bottle/can of soft drink (minimum 300 ml); At least 5 serving pieces of warm cocktail snacks, including vegetarian options; At least 5 serving pieces of cold cocktail snacks, including vegetarian options; At least 4 pieces of cocktail desserts; At least 1 fresh fruit; The Contractor should prepare at least 3 versions of the lunch menu. The menus should be sent by the Contractor to the Contracting Authority for approval at least 5 working days prior to the meeting. The catering services should include professional staff for serving of the cocktail drinks and snacks; - Organization and payment of three coffee breaks for minimum 20 people at the venue of the meeting. Minimum content of the menu for coffee breaks for each participant - coffee / tea-standard quantity, mineral water - 500 ml/ Soft drink - 250 ml, crackers and cookies - 200 g; - Organization and payment of dinner for minimum 20 persons - minimum content of the menu for a dinner for each participant: mineral water - 500 ml; soft drink - 250 ml; wine – 250 ml; salad - 250 g; appetizers - hot bites/ meat and fish delicacies with a total weight 150 g; mainly meat dish - 300 g; dessert. Dinner shall be organized in the restaurant of the selected accommodation hotel or nearby. |

Task 3: Registrations to one (1) international scientific conference and at least one sectoral fair/conference, to present the results of the project

| Time/place: | Forecast period for conduct of the event: September 2018/ July 2019 in Skopje and Balkan Med region countries. |
| --- | --- |
| Service 2.1: | International scientific conference |
| Service description: | Organization and payment of participation at an International conference in Balkan Med region countries and publishing and presentation of a paper presenting project results. |
| Service 2.2: | National sectoral fair/conference |
| Service description: | Organization and payment of publishing and presentation of a project results at least one national sectoral fair/conference. |

Task 4: Open-access publication in one (1) journal

| Time/place: | Forecast period for conduct of the event: September 2018/ July 2019 in any country. |
| --- | --- |
| Service 2.1: | Open-access journal |
| Service description: | Organization and payment of publishing a paper presenting project results at one (1) Open-access journal. |

Notes:

- The Contractor should ensure the participation of at least one representative at each one event in Skopje who will guarantee the timely and qualitative conduction of the envisaged activities.

- The sustainability and dissemination of project results, planned to be conducted within the project will be ensured during the events. The Contractor must also comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. >

The Contractor must also comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. >

## Project management

### Responsible body

Responsible body for this service contract will be the Contracting Authority specified above.

### Management structure

### The effective management of the project will be ensured by the Contracting Authority.

The project manager, Prof. Marija Kacarska will be in charge for the overall coordination.

### Facilities to be provided by the Contracting Authority and/or other parties

No facilities or equipment will be provided by the Contracting Authority.

# LOGISTICS AND TIMING

## Location

The project will be implemented at the territory of Skopje, FYROM and other countries of Balkan-Med region.

## Start date & Period of implementation of tasks

The intended start date is 15.03.2018 and the period of implementation of the contract will be 17 months from this date, but not later than 31.07.2019. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English language:

- Draft final report shall be submitted no later than 5 days after the end of the period of implementation of each task.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 5 days after receipt of comments on the draft final report. This report should provide conclusions and clear evidences on the implementation of all requested services. The final report must be provided along with the corresponding invoice.

The reports provided by the Contractor should be prepared in English language and submitted in the following copies:

- 1 (one) original, duly signed, stamped and dated by the legal representative of the Contractor and

- 1 (one) electronic version.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The qualitative indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manner as required in these Terms of Reference”.

The following quantitative results are to be achieved:

### Indicators related to the organization of a one-day workshop for minimum 50 participants in Skopje

- Provided adequate space;

- Catering services (lunch and coffee break) provided.

### Indicators related to the organization of a three-day project meeting for minimum 20 participants in Skopje

- Adequate accommodation for project partners participating at the meeting booked;

- Adequate conference room provided;

- Catering services (lunches, coffee breaks and dinner) provided;

The indicators are specified as related to each type of services, to be provided:

- Rented of 2 halls - for one minimum 50 participants 1-day event and for one minimum 20 participants 3-days event;

- Rented and provided audio/video equipment for the events;

- Provided Catering services for the following events:

- 1-day Workshop in Skopje – more than 50 persons;

- 3-day project meeting in Skopje – minimum 20 persons.

### Indicators related to the organization of registrations to 1 international scientific conference and at least one sectoral fair/conference

- Search and find adequate conferences / fair and payment of the participation;

- Paying for publishing the paper presenting the project results;

## Special requirements

The communication between the Contractor and the Contracting Authority must be in writing. The Contracting Authority will appoint the Project manager as a contact person for the contract (point 4.3.3. of this document).